## Sheet1
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Preconditions | Expected Results | Actual Results | Status | Executed Date | Comments (if any)
SCN-001 | Verify product catalog | TC-001 | Verify product list display | 1. Navigate to product catalog 2. Check items (eggs, birds, feed, equipment) 3. Open product details page | User logged in or guest | Products show with correct name, price, availability | Product catalog displayed correctly with names, prices, and availability. | Pass | 2025-08-20
|  | TC-002 | Verify filtering & sorting in catalog | 1. Open catalog 2. Apply filter (e.g., by category) 3. Sort by price | At least 10 products available | Filter and sort applied correctly | Filter applied but result is not sorted by price | Fail | 2025-08-20 | Sorting function not working.
SCN-002 | Verify shopping cart & checkout | TC-003 | Verify add/remove items in cart | 1. Select product 2. Add to cart 3. Update quantity 4. Remove product | Product available in stock | Cart updates correctly | Cart updates correctly | Pass | 2025-08-20
|  | TC-004 | Verify checkout flow | 1. Add product to cart 2. Proceed to checkout 3. Enter delivery details 4. Confirm order | User has valid address | Order submitted, confirmation displayed | Failed to place order | Fail | 2025-08-20
SCN-003 | Verify service booking | TC-005 | Verify booking delivery service | 1. Navigate to booking page 2. Select “Book this service” 3. Pick time slot 4. Confirm booking | User logged in | Booking confirmation displayed | Failed to confirm booking | Fail | 2025-08-20
|  | TC-006 | Verify booking farm visit | 1. Select “Farm Visit” 2. Choose date & time 3. Confirm booking | User logged in | Service booking success message shown | Failed to confirm booking | Fail | 2025-08-20
|  | TC-007 | Verify booking veterinary service | 1. Select “Veterinary Service” 2. Choose date 3. Confirm booking | User logged in | Service booking confirmed with reference number | Failed to confirm booking | Fail | 2025-08-20
SCN-004 | Verify payment methods | TC-008 | Verify mobile money payment | 1. Add product to cart 2. Select Mobile Money 3. Complete transaction | Active mobile money account | Payment successful, receipt generated | Payment is not successful | Fail | 2025-08-20
|  | TC-009 | Verify card payment | 1. Add product to cart 2. Select Card Payment 3. Enter valid card 4. Confirm payment | Valid debit/credit card | Payment successful with receipt | Payment is not successful | Fail | 2025-08-20 | Payment gateway integration issue.
|  | TC-010 | Verify cash on delivery | 1. Add product to cart 2. Select Cash on Delivery 3. Place order | COD enabled in system | Order placed, COD marked in order details | Order not placed | Fail | 2025-08-20
SCN-005 | Verify user accounts | TC-011 | Verify user registration | 1. Open registration page 2. Enter details 3. Submit | User not registered | Account created successfully | User is able to create account successfully | Pass | 2025-08-20
|  | TC-012 | Verify user login | 1. Navigate to login 2. Enter credentials 3. Submit | User has valid account | User logged in successfully | New user registered and logged in without issues. | Pass | 2025-08-20
|  | TC-013 | Verify profile update | 1. Login 2. Navigate to profile 3. Edit details 4. Save | User logged in | Profile updated successfully | Profile updates successfully with no issues | Pass | 2025-08-20
|  | TC-014 | Verify order history | 1. Login 2. Navigate to “My Orders” | User has previous orders | Order history displayed correctly | Order history displays correctly | Pass | 2025-08-20
SCN-006 | Verify notifications | TC-015 | Verify order confirmation notification | 1. Place order 2. Check email/SMS/WhatsApp | User has active contact info | Notification received | No notification received | Fail | 2025-08-20 | SMS gateway failure.
|  | TC-016 | Verify booking notification | 1. Book a service 2. Check notifications | User logged in | Booking confirmation notification received | No booking confirmation notification received | Fail | 2025-08-20
SCN-007 | Verify admin dashboard | TC-017 | Verify inventory management | 1. Login as admin 2. Update inventory 3. Save changes | Admin logged in | Inventory updated | Inventory updated | Pass | 2025-08-20
|  | TC-018 | Verify order management | 1. Login as admin 2. Navigate to orders 3. Update order status | Admin logged in | Order status updated | Order status updated | Pass | 2025-08-20
|  | TC-019 | Verify service scheduling | 1. Login as admin 2. Navigate to service scheduling 3. Adjust timings | Admin logged in | Service schedules updated | Service schedules updated | Pass | 2025-08-20
SCN-008 | Verify home page | TC-020 | Verify home page loads | 1. Open home page | Website is up | Homepage loads with banners, links, featured products | Homepage is responsive | Pass | 2025-08-20
SCN-009 | Verify search bar | TC-021 | Verify product search | 1. Enter keyword in search bar 2. Press search 3. Check results | Products available in catalog | Relevant results displayed | Relevant results displayed | Pass | 2025-08-20